## Daily File Testing Issues
ALD Taskforce : Issues Identified During Group - wide Testing of the Daily Loan and Non-cash Collateral Files. July - September, 2006
| Date raised | Issue Name | Issue Description | Resolution | Date Resolved
1 | 2006-07-10 | Confidentiality agreement | Counterparties have not executed confidentiality agreements. Test files cannot be sent until the confidentiality agreements have been signed or another agreement is developed. | A broker-dealer should ensure that all necessary confidentiality agreements have been executed prior to commencing testing. | 2006-07-17
2 | 2006-09-07 | System problem | DTCC experienced a system problem, which caused some jobs to be abandoned. | resolved on 9-11. This problem will not occur in production. | 2006-09-11
3 | 2006-09-13 | DTCC U system transmission problems | SunGard reported having problems transmitting files to the DTCC U system (test system). | DTCC is looking into it, the issue appears to be an NDM problem. The NDM vendor was contacted. While there was no determination on what had caused the problem, the problem did not occur again on following days. | 2006-09-13
4 | 2006-08-11 | File Sending problem | An agent lender experienced a problem sending the daily files. | The problem was related to a corrupted back up of the original file. Secondary back up was restored. Normal transmission has been resumed with the 7/31 file. | 2006-08-15
5 | 2006-08-03 | Broker-dealers who do not need to receive the ALD file | An agent lender had a problem excluding borrowers who do not have open trades and do not need to receive files on a given day. | The lender developed an override for the system with SunGard in order to be able to generate and transmit files only to those broker-dealers who have open positions. | 2005-09-12
6 | 2006-08-30 | Receiving files from DTCC | A broker-dealer connecting directly to DTCC is experiencing an issue receiving agent lenders files from DTCC. The issue is related to how they are connected to DTCC. | The broker-dealer has determined that the issue is on their side, their connection to DTCC does not remain for long enough time to get all the files (times out after 5 min). This is a router issue, expected to be resolved by 9-1-06. | 2006-09-01
7 | 2006-07-13 | Missing internal tax id issue | A report was not generated for one broker-dealer overnight, because the BD's internal tax id was not registered on the Loanet system. When this tax id is missing or invalid there will be NO file generated by SunGard. This was also causing the broker-dealer to not see some of its international trades. | The broker has registered their tax ID into Loanet. SunGard confirmed this on 7/18 and is now able to generate a file. | 2006-07-18
8 | 2006-08-29 | Timing of sending BD's files to SunGard | An agent lender would like to be able to submit its own BD files to SSF before the 8 pm deadline. | SSF can process files sent before 8 pm. However, agent lenders should be aware of time constraints related to "switching the calendar" on the SSF hub. | 2006-08-31
9 | 2006-08-09 | Broker-dealer "unavailable" status at EquiLend | EquiLend experienced an issue with at least one broker-dealer who uses EquiLend for services outside of ALD; because that BD has set themselves up as "unavailable" no ALD files were being passed to them. | EquiLend worked with the broker dealer to resolve this situation. To avoid this problem, broker-dealers (using EquiLend for services other than ALD) should switch themselves to "available" on the EquiLend system. EquiLend is not going to make changes to their functionality. | 2006-08-09
10 | 2006-07-10 | Numeric fields formatting inconsistency | Several agent lenders experienced problems during testing due to numeric fields formatting. Files which did not follow the agreed formats were rejected by the vendor. | The taskforce confirmed the agreed standards for fields formatting. All firms should refer to the technical specifications document to ensure that they have coded everything correctly. | 2006-07-13
11 | 2006-08-10 | Files transmitted/receive late | During testing, broker-dealers complained that they were receiving their reconciliation reports late from SunGard; SunGard reported that agent lender files were coming in late to SunGard, thus causing delay in producing the reports; As the files were being sent only at borrower's request, the agent lenders reported that they did not receive those requests until late, and therefore did not send the files until late in the morning/mid-day. | The issue was resolved by imposing a 9am deadline for agent lenders to send the files. | 2006-08-10
12 | 2006-06-27 | "Current or yesterday's Close of business date" validation | SunGard had a validation for the “current or yesterday’s COB date” on the daily loan and non-cash collateral files which was causing any agent lenders' files with a date other than yesterday's or today's to be rejected by SunGard. | SunGard successfully removed the "yesterday or current COB date" validation in the testing region. With this change SunGard will be able to receive test files from agent lenders, regardless of the business date. Each file received will now be treated as a current business day's file. However, in production this validation will still be performed, and only files with current or yesterday's COB date will be accepted. | 2006-07-17
13 | 2006-08-07 | Sending firm ID on header does not match sending firm ID on detail record | One agent lender sent files with a mismatch of the sending firm ID between the header and detail sections of the record. | Resolved. The issue was a result of files being erroneously generated while the staging environment was undergoing its nightly database refresh. | 2006-08-09
14 | 2006-07-10 | Missing "Principal Lender ID" | A broker-dealer noted that on some records coming from one agent lender, the "Principal Lender ID" was missing. The agent reported experiencing a mapping issue internally, causing some IDs to be dropped and not populated in the ALD file. | The mapping issue was fixed and the agent resent the 6/30/06 test file on 7/13. | 2006-07-17
15 | 2006-09-14 | Master File | SunGard has an issue producing the master file reports. Has worked on it over the past day. | Fix was put in place on 9/22/06 | 2006-09-22
16 | 2006-09-14 | Cash wash issues | A broker-dealer was not seeing the amount of cash collateral on the borrow pledged from one particular agent lender. It was established that this lender uses Global 1. | Global 1 surveyed other clients, there are only 2 which handle cash wash, and the problem is with just one agent lender, so it was determined that this is not a vendor related issue. The broker-dealer and agent lender were left to handle this bi-laterally. | 2006-09-14
17 | 2006-09-18 | Reconciliation breaks - "lot size differences" | A broker-dealer and agent lender agree on the total amount of securities borrowed and collateral provided, however there is a mis-match on the number of contracts each side has associated with these securities. This could be a result of returns or re-allocations, where the agent lender might have closed and re-opened a loan due to a re-allocation, but the broker dealer knows it as one contract. Also, certain agent lenders book US Fixed Income trades as an entire lot while the borrowers book the trade in the lots as delivered by the agent lender. As an example, if a borrower requests 150mm of a bond the Agent Lender may book it as a 150mm trade but deliver it as three 50mm pieces. In this case, the borrower will book the trade as three 50mm pieces, therefore causing the lot break. | Broker-dealers are handling these differences by conducting an additional validation at the security level to ensure that at the security both the securities borrowed and collateral are in balance. | 2006-09-18
18 | 2006-09-14 | Duplicate records in the non-cash file | BD receiving duplicate records in the non-cash collateral file. | Agent lender applied a code change to resolve this issue. | 2006-09-18
19 | 2006-09-13 | Invalid Asset ID | SunGard and broker-dealers were seeing many "invalid asset ID" errors. A broker-dealer should work with their agent lenders and vendor to ensure consistency in the formatting of security IDs, especially for SEDOLs and QUICKs. | SunGard updated their security master, which caused many of these errors to go away. A small number of these remain, due to corporate actions where an agent may assign a "dummy" ID to a security. Also with international securities, sometimes firms may be using a different SEDOL number for the same security, as SEDOL is not universal, but rather country specific number. | 2006-09-18
20 | 2006-08-08 | Borrower settlement Location (BSL) field | Some vendors did not code for the BSL field to be included, as it was noted as "optional" on the file specification. However, during testing it became clear that certain broker-dealers who use one tax ID, but multiple DTCC IDs for their trades require this field in order to determine which trades should go to which internal business unit or what type they are (e.g. fixed income vs. international, etc). | Global 1 and WorldLend have implemented changes in their codes to all for this field to be populated by their agent lender users. A broker-dealer requiring the BSL field should make sure to communicate with their agent lenders and test their ability to provide that information. | 2006-08-14
21 | 2006-09-07 | Missing trade allocations | Agent lender files came in with missing trade allocations. | Firms resolved bi-laterally. | 2006-09-12
22 | 2006-08-01 | Allocation Break | The sum of the street side allocation values are off by a factor of 10. | The problem was on the agent lender's side and has been resolved as of 8/3. | 2006-08-03
23 | 2006-08-31 | Missing securities | A broker-dealer reported that some securities were missing from an agent lender's file that came in on 8-30-06 | The agent lender has resolved the problem which was occurring with one broker-dealer. | 2006-09-01
24 | 2006-09-05 | Tri-party collateral field | An agent lender had a problem with formatting of the tri-party collateral information, and additionally with the tri-party field content. | This was an internal issue related to one agent lender, and it was subsequently resolved. | 2006-09-18
25 | 2006-08-29 | Tri-party amounts differ from expected | An agent lender received feedback from several of its borrowers that the amount indicated in the tri-party amount field in the non-cash collateral loan differs from what borrowers had expected to see in that field. | This was due to the agent lender failing to populate the field properly. Changes have been made to resolve. | 2006-08-29
26 | 2006-07-27 | Tri-Party Amount | Are agent lenders going to provide the actual amount for tri-party collateral or projected amount? What will come through from Global 1 and WorldLend? | The agent lenders surveyed believe that the difference between the projected and actual amounts is generally minimal with respect to the total collateral. Broker-dealers should not need to treat the tri-party amount differently based on it being projected or actual. Broker-dealers concerned with the treatment of the tri-party collateral amount should contact each of their agent lenders directly for further detail on the lender’s process. | 2006-08-08
27 | 2006-07-28 | Sending both amount and % | In the 6/30 test file sent on the evening of 7/27, an agent provided both tri-party % and tri-party amount. | The ALD file can handle either % or amount, the agent lender has made a change and will send only percentage in the future. | 2006-07-28
28 | 2006-09-12 | Cash collateral | A broker-dealer was noticing breaks on the cash collateral information coming from one agent lender. | Resolved bi-laterally with the agent lender. | 2006-09-13
29 | 2006-09-05 | Penny differences | Many broker dealers are seeing penny differences in the security quantity and collateral amounts. | These breaks occur because of different rounding techniques used by the two parties. Each firm is determining its own level of materiality, and choosing how to handle these breaks. Borrowers using the SSF ALDOP reconciliation functionality will continue to receive reports including these breaks, however they will be segregated from the larger material breaks. | 2006-09-13
30 | 2006-08-31 | Penny breaks due to "0" value in the collateral value field. | Penny breaks due to $0.01 in the "Cash collateral amount" field These breaks are identified during reconciliation, and are being invalidated by Contract Compare since the actual broker-dealer loan has a zero amount but the agent lender is forcing $0.01 in place of zero for collateral types “C” and “M”. Related to issue #1, this is also a source of penny breaks. | A reminder has been sent to agent lenders to change their processing to allow a zero value, if necessary on cash and mixed collateral loans and schedule the required modification. It is uncertain when all agent lender can make this change, given their own internal technology plans. Broker-dealers would like to treat these the same way as other penny breaks. | 2006-09-01
31 | 2006-08-31 | File sent for the wrong entity | A broker-dealer who borrowers through two separate entities realized that loans coming from an agent lender went to the wrong entity. | The agent executed a code change to fix this issue. | 2006-09-11
32 | 2006-09-11 | Sending one file to two separate entities | A broker dealer who has two separate legal entities they borrow through is receiving one file for both entities from one agent lenders. | The agent lender has made a change, this problem should not occur again. | 2006-09-08
33 | 2006-07-19 | Multiple files | Agent lender is sending multiple files (four-five) on a given day to one broker-dealer, and the broker cannot determine which one is the correct one. The agent lender revealed that they separate counterparties by the different types of loans (i.e. equity, agencies, term loans, etc.), and send a separate file for each product. This explains the multiple files. | The agent lender addressed the issue, and is now producing one file per broker-dealer (legal entity). | 2006-07-27
34 | 2006-09-07 | Missing "99" classification | SunGard's credit approval system did not include the "99" code for supra national entities. | SunGard implemented a fix on 9/12/06. | 2006-09-12
35 | 2006-09-05 | Missing tri-party ID | An agent lender had not included a tri-party ID on the non-cash file. | Fixed on 9-7 | 2006-09-07
36 | 2006-07-13 | Missing Non-Cash Collateral file | A broker-dealer was receiving daily loan files containing records with collateral types = N,P or M, but not receiving the Non-Cash Collateral file. Per the spec's, "a type "N", "M" or "P" will indicate to the receiver that there is an additional non-cash collateral detail file that should be received as well." The agent lender revealed that their internal system was not flagged to generate non-cash files for that particular borrower. | The agent lender fixed the problem on 7/27. | 2006-07-27
37 | 2006-09-06 | Loans from unapproved principals | Broker-dealers reported loans allocated to unapproved principals Broker-dealers are receiving daily loan files including allocations to principals which had been rejected, during the re-qualifications process. | Broker-dealers are working with agent lenders to resolve the issue. This could be due to technology errors or a lag in the re-allocation process for rejected principals. This issue is occurring less frequently over time. | 2006-09-08
38 | 2006-09-06 | Daily files sent Sat or Monday | Clarify with the group the expectation for when Friday COB files will be transmitted - Saturday morning or Monday morning? | It is expected that files should be received Friday night and into Sat. morning, however some agent lenders may send the files on Monday morning instead. Both vendors will be operational early Sat morning as well as early Monday morning. | 2006-09-08
39 | 2006-09-05 | Multiple files on the hub | An agent lender reported seeing two files on the SSF hub, when they only sent one. | Issue was resolved with SunGard. | 2006-09-06
40 | 2006-09-05 | Holiday Processing | During the recent Labor day holiday, it was apparent that not having a standard holiday processing schedule will be a problem. | The taskforce has agreed that agent lenders should send a file every week day. If an agent is not able to send a file, they should notify their broker-dealers. On a holiday the file will contain the data from the previous business day. | 2006-09-07
41 | 2006-08-03 | Holiday processing - date in header record | WorldLend users had to manually insert a holiday date in the header as the WorldLend system did not recognize holidays as valid days and was automatically putting the next day's date on the file. | WorldLend has resolved this problem. Agent lenders using that system should be able to send out files on a holiday with the correct calendar date in the header. | 2006-08-14
42 | 2006-08-31 | Currency Break | An agent lender experienced problems with currency breaks. | fixed on 9-5 | 2006-09-05
43 | 2006-08-30 | File fails to load on Loanet | An agent lender has experienced a problem, where Loanet fails to load their daily loan file due to the size of the file. This occurs regardless of the time the file is sent. The agent lender called Loanet to manually reprocess part of the file, in order to fully load it. This sometimes results in the agent's counterparties receiving their daily loan file data twice, which means that they are unable to reconcile. | This was a timing issue on SunGard's side. Their system was going to sleep for some periods in the middle of the file being processed, so parts of the file were being cut off. There is a change being made on 8-30, which should reduce this occurrence. SunGard has also suggesting that the agent lender move to use a PGP encryption which would allow the file to move more quickly through the system. | 2006-08-30
44 | 2006-07-27 | Sub-agents fails | ALD file reconciliation break occurring with failed securities for sub-agents to one agent lender. There was no break in the contract compare. | After consultations with several agent lenders and broker-dealers, the group is of the opinion that the agent lender should always send a file and there should be a principal allocation indicated. It is up to the agent lender to decided whether in the cases of failed sales the principal lender will remain on the loan or whether the agent himself will act as a principal. Most agents keep the original principal on the loan. | 2006-08-04
45 | 2006-09-05 | Collateral value | Taking pre mark-to-market or post mark-to-market values | SunGard expects to take the pre-mark information. There were no objections to this approach. | 2006-09-05
46 | 2006-07-07 | Type 2 records count | In one case, the number of Principal allocations does not match the count in the "Number of Type 2 Records" field. In another case, the sum of the quantities in record Type 2 did not equal the (total) quantity value in record Type 1. In a their case, the daily loan file was missing record Type 2. As stated in the technical specifications, each Type 1 record should be followed by a Type 2 record. Each Type 2 record for loan should bear the same trade ID as the one in the Type 1 record. | Both of these were agent lender related issues and have been resolved by each agent. | 2006-07-20
47 | 2006-07-13 | Duplicate records w/ prepaid trades | An agent lender using Global 1 had an issue with generating duplicate records for foreign pre-paid trades. | A solution was worked out with Global 1. | 2006-07-14
48 | 2006-08-31 | Moving credit limit data from production to test system | On 8-31 SunGard moved client data on credit limits from production to the test system. There are some issues running credit reports, the reports taking a long time to run, and some may be missing. In the future, SunGard will look for an optimization of the process for generating the reports. This is affecting only the credit reports, all other repots should be available with no problem. | The issue is resolved. Broker-dealers have to change one of the parameters on their set up in order for the system to work properly. Anyone having difficulty with the credit functionality should contact the SunGard helpdesk. | 2006-09-01
49 | 2006-08-28 | Credit limit set up | There is confusion as to how broker-dealers should set up the credit limits on the SunGard hub. It is not clear whether limits should be set up in testing or in production, and how/what brokers will be able to change once they have initially input all limits in production. One BD reported that it is difficult to locate a principal lender on the function, a search can be performed by tax ID only. | SunGard is working with its clients to provide more clear instructions on the process. | 2006-08-31
50 | 2006-08-21 | Value for MBS | One agent lender was providing the original value plus a factor for mortgage backed securities. | As per the agreed standard noted in the daily file technical specifications, the agent lender has changed how they calculate and provide the value. | 2006-08-22
51 | 2006-08-11 | Securities pricing | One agent lender was experiencing a problem with pricing of securities, which is affected the sent files. This is related to one source file which was not archived. | The agent identified the root of the problem, but due to the fact that one source file was not archived, this problem continued throughout testing. | 2006-08-15
52 | 2006-07-28 | Pending loans being sent out with open loans | Data for loans where neither securities nor cash had settled were being added and sent out with the open loans on the daily file. | This has been fixed. | 2006-07-28
53 | 2006-07-08 | Disclosed vs. Non-Disclosed accounts | In one case, an agent lender was classifying principals as disclosed when they should have been non-disclosed. In another case, several broker-dealers have noted that they are receiving accounts flagged as "N" where they should have been marked "D" | Each broker-dealer and agent lender should review the accounts in question and agree on which accounts are disclosed and which ones are not. | 2006-07-14
Most Common Issues reported by the Vendors during testing
| Date Raised | Number of times reported | Issue Name
| 8/29, 8/30 | 2 | Amount breaks
| 9/1, 9/11 | 2 | Backlog in producing daily reports
| 8/8 | 2 | Borrower settlement Location (BSL) field Issues
| 8/31 | 1 | Currency breaks
| 8/21 | 1 | Data Errors
| 8/28, 8/31 | 3 | Difficulty in setting up the credit limit functionality on SSF
| 8/30 | 2 | File processing - (errors from DTCC)
| 9/7 | 5 | File processing - (system/transmission problems), DTCC, SSF, Agent Lenders
| 2006-08-03 | 1 | Holiday Date / Header Date
| 8/16 - 8/23 | 22 | Invalid Asset ID
| 2006-07-17 | 4 | Invalid Collateral Type ID
| 8/22 - 8/23 | 2 | Invalid Currency
| 8/18, 8/21 | 4 | Invalid CUSIP ID
| 2006-07-25 | 1 | Invalid Dummy CUSIP ID
| 8/29 | 1 | Invalid Market Value Date
| 8/29 - 9/12 | 5 | Invalid Principal ID
| 8/18 - 8/23 | 22 | Invalid SEDOL ID
| 8/22 & 8/23 | 9 | Invalid Trade ID
| 8/29, 9/6 | 2 | Loans from unapproved principals
| 8/18 - 8/23 | 3 | Missing Cash Pool Amounts
| 8/16 - 8/23 | 7 | Missing collateral amount
| 8/18 | 3 | Invalid or Missing ISIN ID
| 8,18 - 8/23 | 4 | Missing LOC Amounts or LOC Bank ID
| 8/16 & 8/22 | 1 | Missing Principal Asset ID
| 8/18 - 8/23 | 3 | Missing Quantities
| 8/29 | 1 | Missing Sending Firm Id
| 8/31 - 9/8 | 5 | Missing Tri-party Account/Reference #
| 8/29 - 9/13 | 7 | Missing Type 2 Records - Trade Allocations
| 8/21 | 1 | Multiple Files
| 8/29 | 1 | Rounding Issue - (collateral file)
| 7/14 | 2 | Tri-Party Allocation Interpretation
| 8/21 | 1 | Type 1 record does not equal Type 2 record